## Sheet1
www.goodoldmanoj.com
Burn down chart
Project | Story | Task | Start | Day 12 | Day 11 | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
Presentasi Capres | Intro | Task 1.0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
Presentasi Capres | Masa Kecil JK | Task 1.1 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Presentasi Capres | Masa Karir JK | Task 1.2 | 4 | 4 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Presentasi Capres | Masa Studi JK | Task 1.3 | 4 | 4 | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Presentasi Capres | Masa Kecil Jokowi | Task 1.4 | 4 | 4 | 4 | 4 | 3 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0
Presentasi Capres | Masa Kuliah dan Berwirausaha | Task 1.5 | 4 | 4 | 4 | 4 | 3 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0
Presentasi Capres | Pendidikan Jokowi | Task 1.6 | 4 | 4 | 4 | 4 | 3 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0
Presentasi Capres | Masa Kecil Prabowo | Task 1.7 | 4 | 4 | 4 | 4 | 3 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0
Presentasi Capres | Masa Kemiliteran | Task 1.8 | 4 | 4 | 4 | 4 | 3 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0
Presentasi Capres | Karir Prabowo | Task 1.9 | 4 | 4 | 4 | 4 | 3 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0
Presentasi Capres | Karir Prabowo Bisnis | Task 1.10 | 4 | 4 | 4 | 4 | 3 | 3 | 2 | 2 | 1 | 1 | 0 | 0 | 0
Presentasi Capres | Kelahiran Hatta | Task 1.11 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 2 | 1 | 1 | 0 | 0 | 0
Presentasi Capres | Masa karir Hatta | Task 1.12 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 2 | 1 | 1 | 0 | 0 | 0
Presentasi Capres | Pendidikan Hatta | Task 1.13 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 2 | 1 | 1 | 0 | 0 | 0
Presentasi Capres | Kerangka Awal | Task 1.14 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 2 | 1 | 1 | 0 | 0 | 0
Presentasi Capres | Styling | Task 1.15 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 2 | 1 | 1 | 0 | 0 | 0
Presentasi Capres | Ending | Task 1.16 | 4 | 4 | 6 | 4 | 4 | 3 | 2 | 2 | 1 | 1 | 0 | 0 | 0
Ideal - Remaining efforts in uninterrupted working hours |  |  | 72 | 66 | 60 | 54 | 48 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 1
Actual - Remaining efforts in uninterrupted working hours |  |  | 72 | 68 | 58 | 52 | 45 | 37 | 30 | 26 | 18 | 13 | 0 | 3 | 0
Note on H5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on I5: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered